## Slide 1: Chapter 17
Project Management
Operations Management
FOURTEENTH EDITION
William J. Stevenson

## Slide 2: Chapter 17: Learning Objectives
You should be able to:
  LO 17.1 Describe the project life cycle
  LO 17.2 Discuss the behavioral aspects of projects in terms of project personnel and the project manager
  LO 17.3 Name the six key decisions in project management
  LO 17.4 Explain the nature and importance of a work breakdown structure in project management
  LO 17.5 Give a general description of PERT/CPM techniques
  LO 17.6 Construct simple network diagrams
  LO 17.7 Analyze networks with deterministic times
  LO 17.8 Analyze networks with probabilistic times
  LO 17.9 Describe activity “crashing” and solve typical problems
  LO 17.10 Discuss the advantages of using PERT and potential sources of error
  LO 17.11 Discuss the key steps in risk management

## Slide 3: Projects
LO 17.1
Projects
  Unique, one-time operations designed to accomplish a specific set of objectives in a limited time frame
  Examples:
    The Olympic Games
    Producing a movie
    Software development
    Product development
    ERP implementation

## Slide 4: The Nature of Projects
LO 17.1
Projects go through a series of stages – a life cycle
Projects bring together people with a diversity of knowledge and skills, most of whom remain associated with the project for less than its full life
Organizational structure affects how projects are managed

## Slide 5: Project Life Cycle 1
LO 17.1
Initiating
Planning
Executing
Monitoring and Controlling
Closing

## Slide 6: Project Life Cycle 2
LO 17.1
FIGURE 17.1 Project life cycle
Access the text alternative for slide images.

## Slide 7: Project Management Decisions
LO 17.3
Project success depends upon making key managerial decisions over a sequence of steps:
  Deciding which projects to implement
  Selecting the project manager
  Selecting the project team
  Planning and designing the project
  Managing and controlling project resources
  Deciding if and when a project should be terminated

## Slide 8: Project Manager
LO 17.2
The project manager is ultimately responsible for the success or failure of the project
The project manager must effectively manage:
  The work
  The human resources
  Communications
  Quality
  Time
  Costs

## Slide 9: Project Management Body of Knowledge
LO 17.3
The Project Management Institute (PMI) has developed a list of 10 areas of knowledge:
  Managing integration
  Managing scope
  Managing time/schedule
  Managing costs
  Managing quality
  Managing human resources
  Managing communication
  Managing risk
  Managing procurement
  Managing stakeholders

## Slide 10: The Project Management Triangle
LO 17.3

## Slide 11: Behavioral Issues
LO 17.3
Behavioral problems can be created or exacerbated by
  Decentralized decision making
  Stress of achieving project milestones on time and within budget
  Surprises
The team must be able to function as a unit
  Interpersonal and coping skills are very important
  Conflict resolution and negotiation can be an important part of a project manager’s job

## Slide 12: Avoiding Problems
LO 17.3
Many problems can be avoided or mitigated by:
  Effective team selection
  Leadership
  Motivation
  Maintaining an environment of
    Integrity
    Trust
    Professionalism
  Being supportive of team efforts

## Slide 13: Project Champion
LO 17.3
Project champion
  A person who promotes and supports a project
    Usually resides within the organization
    Facilitate the work of the project by ‘talking up’ the project to other managers who might be asked to share resources with the project team as well as employees who might be asked to work on parts of the project
    The project champion can be critical to the success of a project

## Slide 14: Work Breakdown Structure (WBS)
LO 17.4
WBS
  A hierarchical listing of what must be done during a project
    Establishes a logical framework for identifying the required activities for the project
      Identify the major elements of the project
      Identify the major supporting activities for each of the major elements
      Break down each major supporting activity into a list of the activities that will be needed to accomplish it

## Slide 15: WBS: Working with Gantt Charts 1
LO 17.4

## Slide 16: WBS: Working with Gantt Charts 2
FIGURE 17.3 Gantt chart for bank example
Access the text alternative for slide images.

## Slide 17: PERT and CPM
LO 17.5
PERT (program evaluation and review technique) and CPM (critical path method) are two techniques used to manage large-scale projects
By using PERT or CPM managers can obtain:
  A graphical display of project activities
  An estimate of how long the project will take
  An indication of which activities are most critical to timely project completion
  An indication of how long any activity can be delayed without delaying the project

## Slide 18: Network Diagram
LO 17.6
Network diagram
  Diagram of project activities that shows sequential relationships by use of arrows and nodes
  Activity on arrow (AOA)
    Network diagram convention in which arrows designate activities
  Activity on node (AON)
    Network convention in which nodes designate activities
      Activities
        Project steps that consume resources and/or time
      Events
        The starting and finishing of activities

## Slide 19: Network Conventions
LO 17.6
TABLE 17.2 Network conventions

## Slide 20: Deterministic Time Estimates
LO 17.7
Deterministic
  Time estimates that are fairly certain
Probabilistic
  Time estimates that allow for variation

## Slide 21: Early Start, Early Finish
LO 17.7
Finding ES and EF involves a forward pass through the network diagram
  Early start (ES)
    The earliest time an activity can start
    Assumes all preceding activities start as early as possible
      For nodes with one entering arrow
        ES = EF of the entering arrow
      For activities leaving nodes with multiple entering arrows
        ES = the largest of the largest entering EF
  Early finish (EF)
    The earliest time an activity can finish
      EF = ES + t

## Slide 22: Late Start, Late Finish
LO 17.7
Finding LS and LF involves a backward pass through the network diagram
  Late Start (LS)
    The latest time the activity can start and not delay the project
      The latest starting time for each activity is equal to its latest finishing time minus its expected duration:
        LS = LF − t
  Late Finish (LF)
    The latest time the activity can finish and not delay the project
      For nodes with one leaving arrow, LF for nodes entering that node equals the LS of the leaving arrow
      For nodes with multiple leaving arrows, LF for arrows entering node equals the smallest of the leaving arrows

## Slide 23: Slack and the Critical Path
LO 17.7
Slack can be computed one of two ways:
  Slack = LS – ES
  Slack = LF – EF
Critical path
  The critical path is indicated by the activities with zero slack

## Slide 24: Using Slack Times
LO 17.7
Knowledge of slack times provides managers with information for planning allocation of scarce resources
  Control efforts will be directed toward those activities that might be most susceptible to delaying the project
  Activity slack times are based on the assumption that all of the activities on the same path will be started as early as possible and not exceed their expected time
  If two activities are on the same path and have the same slack, this will be the total slack available to both

## Slide 25: Probabilistic Time Estimates 1
LO 17.8
The beta distribution is generally used to describe the inherent variability in time estimates
The probabilistic approach involves three time estimates:
  Optimistic time, (to)
    The length of time required under optimal conditions
  Pessimistic time, (tp)
    The length of time required under the worst conditions
  Most likely time, (tm)
    The most probable length of time required

## Slide 26: The Beta Distribution
LO 17.8
Access the text alternative for slide images.

## Slide 27: Probabilistic Time Estimates 2
LO 17.8
The expected time, te ,for an activity is a weighted average of the three time estimates:
The expected duration of a path is equal to the sum of the expected times of the activities on that path:

## Slide 28: Probabilistic Time Estimates 3
LO 17.8
The standard deviation of each activity’s time is estimated as one-sixth of the difference between the pessimistic and optimistic time estimates. The variance is the square of the standard deviation:
Standard deviation of the expected time for the path:

## Slide 29: Knowledge of Path Statistics
LO 17.8
Knowledge of expected path times and their standard deviations enables managers to compute probabilistic estimates about project completion such as:
  The probability that the project will be completed by a certain time
  The probability that the project will take longer than its expected completion time

## Slide 30: Path Probabilities
LO 17.8
Calculating path probabilities involves the use of the normal distribution
Although path activities are represented by the beta distribution, the path distribution can be represented by a normal distribution

## Slide 31: Determining Path Probabilities
LO 17.8
Access the text alternative for slide images.

## Slide 32: Project Completion Time
LO 17.8
A project is not complete until all project activities are complete
It is risky to only consider the critical path when assessing the probability of completing a project within a specified time
  To determine the probability of completing the project within a particular time frame
    Calculate the probability that each path in the project will be completed within the specified time
    Multiply these probabilities
  The result is the probability that the project will be completed within the specified time

## Slide 33: Assumption: Independence
LO 17.8
Independence
  Assumption that path duration times are independent of each other
    Requires that
      Activity times are independent
      Each activity is on only one path
    The assumption of independence is usually considered to be met if only a few activities in a large project are on multiple paths

## Slide 34: Simulation
LO 17.8
When activity times cannot be assumed to be independent, simulation is often used
  Repeated sampling is used
    Many passes are made through the project network
    In each pass, a random value for each activity time is selected based on the activity time’s probability distribution
    After each pass, the project’s duration is determined
    After a large number of passes, there are enough data points to prepare a frequency distribution of the project duration
    Probabilistic estimates of completion times are made based on this frequency distribution

## Slide 35: Time-Cost Trade-Offs
LO 17.9
Activity time estimates are made for some given level of resources
It may be possible to reduce the duration of a project by injecting additional resources
  Motivations:
    To avoid late penalties
    Monetary incentives
    Free resources for use on other projects

## Slide 36: Time-Cost Trade-Offs: Crashing
LO 17.9
Crashing
  Shortening activity durations
    Typically, involves the use of additional funds to support additional personnel or more efficient equipment, and the relaxing of some work specifications
  The project duration may be shortened by increasing direct expenses, thereby realizing savings in indirect project costs

## Slide 37: Crashing Decisions
LO 17.9
To make decisions concerning crashing requires information about:
  Regular time and crash time estimates for each activity
  Regular cost and crash cost estimates for each activity
  A list of activities that are on the critical path
    Critical path activities are potential candidates for crashing
    Crashing non-critical path activities would not have an impact on overall project duration

## Slide 38: Crashing: Procedure
LO 17.9
General procedure:
  Crash the project one period at a time
  Crash the least expensive activity that is on the critical path
  When there are multiple critical paths, find the sum of crashing the least expensive activity on each critical path
    If two or more critical paths share common activities, compare the least expensive cost of crashing a common activity shared by critical paths with the sum for the separate critical paths

## Slide 39: Crashing Activities
LO 17.9

## Slide 40: PERT: Advantages
LO 17.10
Among the most useful features of PERT:
  It forces the manager to organize and quantify available information and to identify where additional information is needed
  It provides a graphic display of the project and its major activities
  It identifies
    Activities that should be closely watched
    Activities that have slack time

## Slide 41: Sources of Error
LO 17.10
Potential sources of error:
  The project network may be incomplete
  Precedence relationships may not be correctly expressed
  Time estimates may be inaccurate
  There may be a tendency to focus on critical path activities to the exclusion of other important project activities
  Major risk events may not be on the critical path

## Slide 42: Risk Management
LO 17.11
Risks are an inherent part of project management
  Risks relate to occurrence of events that have undesirable consequences such as
    Delays
    Increased costs
    Inability to meet technical specifications

## Slide 43: Risk Management (cont.)
LO 17.11
Good risk management involves
  Identifying as many risks as possible
  Analyzing and assessing those risks
  Working to minimize the probability of their occurrence
  Establishing contingency plans and budgets for dealing with any that do occur

## Slide 44: End of Main Content

## Slide 45: Accessibility Content: Text Alternatives for Images

## Slide 46: Project Life Cycle 2 - Text Alternative
Return to parent-slide containing images.
The graph is low at the initiating stage, which includes goals, specifications, feasibility, tasks, and responsibilities. It begins to increase during the planning stage, which includes schedules, budgets, resources, risks, and staffing. The Execution and Monitoring and Controlling stage has a high level of effort throughout, and includes status reports, changes, quality, manage, monitor and control. The closing stage is where the level of effort drops, and includes the tasks of training the customer, transferring documents, releasing resources, reassigning staff, and lessons learned.
Return to parent-slide containing images.

## Slide 47: WBS: Working with Gantt Charts 2 - Text Alternative
Return to parent-slide containing images.
Across the bottom are the weeks after start of the project (Start to 20), and rows containing each activity. These include: locate new facilities, interview prospective new staff, hire and train staff, select and order furniture, remodel and install phones, furniture received and set up, move in/startup. A bar spans the beginning to end weeks for each activity.
Return to parent-slide containing images.

## Slide 48: The Beta Distribution - Text Alternative
Return to parent-slide containing images.
The timeline starts at 0, then t-sub-0 is the start of the beta distribution. The peak of the beta distribution is at t-sub-m, the most likely time (the mode), then t-sub-e is at the decline of the peak, then t-sub-p (the pessimistic time) is at the right end of the distribution.
Return to parent-slide containing images.

## Slide 49: Determining Path Probabilities - Text Alternative
Return to parent-slide containing images.
A normal distribution shaded from the left to a z-value marked "specified time," with the shaded area marked "probability of comping the path by the specified time." The expected path duration is the mean.
Return to parent-slide containing images.